## Sheet1
GAMEHUB INVENTORY SYSTEM
Members:
Hanz Chester Bacus
Jeastel Mae Maratas
Russell Joshua Palma
Statuses
Todo | In-Progress | Completed | On-hold
| Deliverables | Status | Date Started | Date Finished | Due Date | Assignee | NOTE | August |  |  |  | September |  |  |  | October |  |  |  | November |  |  |  | December
[8 empty] | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4
| Look for Possible Project Title | Completed | 08/20/2024 | 08/20/2024 | 08/21/2024 | Hanz, Jeastel, Russell | bar: August 2
| Finalize Project Proposal and Post on Teams | Completed | 08/21/2024 | 08/21/2024 | 08/21/2024 | Hanz | bar: August 2
| Fill-Up Project Proposal Form | Completed | 08/21/2024 | 08/21/2024 | 08/21/2024 | Jeastel | bar: August 2
| Make ERD | Completed | 2024-04-09 | 2024-05-09 | 2024-05-09 | Hanz | bar: August 4
| System UI-UX on Figma | [5 empty] | On-going revisions
| 1. Log-In Page | Completed | 2024-04-09 | 2024-07-09 | 2024-08-09 | bar: September 1
| Design UI | Completed | 2024-05-09 | 2024-07-09 | 2024-08-09 | Russel | bar: September 1
| Finalize UI/Ux | Completed | 2024-06-09 | 2024-08-09 | 2024-09-09 | Russel | bar: September 1
2. Sign-Up Page
| Design UI | Completed | 2024-06-09 | 2024-10-09 | 2024-11-09 | Russel | bar: September 1
3. Landing Page
| My Account | Completed | 2024-06-09 | 09/14/2024 | 09/16/2024 | Jeastel | bar: September 1
| My Orders | Completed | 2024-06-09 | 09/14/2024 | 09/16/2024 | Jeastel | bar: September 1
| Stored Payment Method | Completed | 2024-06-09 | 09/14/2024 | 09/16/2024 | Jeastel | bar: September 1
| My Reward Points History | Completed | 2024-06-09 | 09/14/2024 | 09/16/2024 | Jeastel | bar: September 1
| Conditions | Completed | 2024-06-09 | 09/14/2024 | 09/16/2024 | Jeastel | bar: September 1
4. Profile Page
| Design UI/UX | Completed | 2024-10-09 | 09/15/2024 | 09/20/2024 | Hanz | bar: September 1
5. Messages Page
| Design UI-UX | Completed | 2024-10-09 | 09/15/2024 | 09/20/2024 | Hanz | bar: September 1
| 6. Store Page |  |  |  |  | Hanz
| Design UI-UX | Completed | 2024-10-09 | 09/15/2024 | 09/20/2024 | Hanz | bar: September 1
7. Cart Page
| Design UI-UX | Completed | 2024-10-09 | 09/15/2024 | 09/20/2024 | Russell | bar: September 1
8. Payment Page
| Design UI-UX | Completed | 2024-10-09 | 09/14/2024 | 09/20/2024 | Hanz | bar: September 1
REDESIGN UI-UX FIGMA
1. Log-In Page
| Design UI | Completed | 09/28/2024 | 09/30/2024 | 09/30/2024 | Russel | bar: September 3 to September 4
| Finalize UI/Ux | Completed | 09/28/2024 | 09/30/2024 | 09/30/2024 | Russel | bar: September 3 to September 4
2. Sign-Up Page
| Design UI | Completed | 09/28/2024 | 09/30/2024 | 09/30/2024 | Russel | bar: September 3 to September 4
3. Landing Page
| My Account | Completed | 09/28/2024 | 09/30/2024 | 09/30/2024 | Jeastel | bar: September 3 to September 4
| My Orders | Completed | 09/28/2024 | 09/30/2024 | 09/30/2024 | Jeastel | bar: September 3 to September 4
| Stored Payment Method | Completed | 09/28/2024 | 09/30/2024 | 09/30/2024 | Jeastel | bar: September 3 to September 4
| My Reward Points History | Completed | 09/28/2024 | 09/30/2024 | 09/30/2024 | Jeastel | bar: September 3 to September 4
| Conditions | Completed | 2024-09-28 | 2024-09-30 | 09/30/2024 | Jeastel | bar: September 3 to September 4
4. Profile Page
| Design UI/UX | Completed | 2024-09-28 | 2024-09-30 | 2024-03-10 | Hanz | bar: September 4
5. Messages Page
| Design UI-UX | Completed | 2024-09-28 | 2024-09-30 | 2024-03-10 | Hanz | bar: September 4
| 6. Store Page |  |  |  |  | Hanz
| Design UI-UX | Completed | 2024-09-28 | 2024-09-30 | 2024-03-10 | Hanz | bar: September 4
7. Cart Page
| Design UI-UX | Completed | 2024-09-28 | 2024-09-30 | 2024-03-10 | Russell | bar: September 4
8. Payment Page
| Design UI-UX | Completed | 2024-09-30 | 2024-09-30 | 2024-03-10 | Russell | bar: September 4
FUNCTIONALITIES
| 1. Log-In Page | Completed | 09/28/2024 | 2024-01-10 | 12/13/2024 | Hanz | bar: September 3 to September 4
| Log in Database | Completed | 09/28/2024 | 2024-10-31 |  | Hanz
| 2. Sign-Up Page | Completed | 09/28/2024 | 2024-01-10 | 12/13/2024 | Jeastel | bar: September 3 to September 4
| Sign up Database | Completed | 2024-09-28 | 2024-10-31 | 2024-12-13 | Hanz
| 3. Landing Page | Completed | 09/28/2024 | 2024-04-10 | 12/13/2024 | Russell | bar: September 3 to September 4
| My Account | Completed | 09/28/2024 | 2024-11-01 | 12/13/2024 | Hanz | bar: October 1 to October 3
| My Orders | Completed | 09/28/2024 | 2024-11-01 | 12/13/2024 | Hanz | bar: October 1 to October 3
0
4. Home Page | bar: October 2 to October 3
| Laptop | Completed | 09/28/2024 | 2024-10-15 | 12/13/2024 | Hanz | bar: October 2 to October 3
| New | Completed | 09/28/2024 | 2024-10-26 | 12/13/2024 | Hanz | bar: October 2 to October 3
| Deals | Completed | 09/28/2024 | 2024-11-02 | 12/13/2024 | Russell | bar: October 2 to October 3
| PC | Completed | 09/28/2024 | 2024-11-02 | 12/13/2024 | Jeastel | bar: October 2 to October 3
| Active | Completed | 2024-10-01 | 2024-11-02 | 2024-11-03 | Jeastel | bar: October 2 to October 3
| - LOL | Completed | 2024-11-01 | 2024-11-18 | 2024-11-03 | Jeastel | bar: October 2 to October 3
| - Cyberpunk | Completed | 09/28/2024 | 2024-11-18 | 12/13/2024 | Russell
| - CS:GO | Completed | 09/28/2024 | 2024-11-18 | 12/13/2024 | Jeastel | bar: October 2 to October 3
| - Fortnite | Completed | 09/28/2024 | 2024-11-18 | 12/13/2024 | Jeastel
| - EldenRing | Completed | 09/28/2024 | 2024-11-18 | 12/13/2024 | Russell | bar: October 2 to October 3
| - Valorant | Completed | 09/28/2024 | 2024-11-18 | 12/13/2024 | Jeastel
| - Apex | Completed | 09/28/2024 | 2024-11-18 | 12/13/2024 | Jeastel | bar: October 2 to October 3
| Phones | Completed | 09/28/2024 | 2024-11-02 | 12/13/2024 | Russell
| - Gaming | Completed | 09/28/2024 | 2024-11-02 | 12/13/2024 | Jeastel | bar: October 2 to October 3
- Non-gaming
| Accessories | Completed | 09/28/2024 | 2024-11-18 | 12/13/2024 | Hanz | bar: October 2 to October 3
| 4. Profile Page | In Progress | 09/28/2024 |  | 12/13/2024 | Hanz
| 5. Messages Page | In Progress | 09/28/2024 |  | 12/13/2024 | Hanz | bar: October 2 to October 3
| 6. Store Page | Completed | 09/28/2024 | 2024-11-18 | 12/13/2024 | Hanz | bar: October 2 to October 3
| 7. Cart Page | In Progress | 09/28/2024 |  | 12/13/2024 | Hanz | bar: October 2 to October 3
| 8. Order Page | In Progress | bar: October 2 to October 3
| 9. Payment Page | In Progress | 09/28/2024 |  | 12/13/2024 | Jeastel | bar: October 2 to October 3
| 10. Searches Functionalty | Completed | 09/28/2024 | 2024-11-22 | 12/13/2024 | bar: October 2 to October 3
| UI-UX | In Progress | 09/28/2024 |  | 12/13/2024 | Russell | bar: October 2 to October 3
|  | To Do | 09/28/2024 |  | 12/13/2024 | Hanz | bar: October 2 to October 3
| 1. Log-In Page | To Do | 09/28/2024 |  | 12/13/2024 | Jeastel
|  | To Do | 09/28/2024 |  | 12/13/2024 | Hanz
| 2. Sign-Up Page | To Do | 09/28/2024 |  | 12/13/2024 | Russell
|  | To Do | 09/28/2024 |  | 12/13/2024 | Jeastel
3. Landing Page | bar: October 2 to October 3
| My Account | In Progress | 09/28/2024 |  | 12/13/2024 | Hanz
My Orders | bar: October 2 to October 3
Stored Payment Method
| My Reward Points History | In Progress | 09/28/2024 |  | 12/13/2024 | Jeastel | bar: October 2 to October 3
Conditions
|  | To Do | 09/28/2024 |  | 12/13/2024 | Russell | bar: October 2 to October 3
4. Home Page
|  | To Do | 09/28/2024 |  | 12/13/2024 | Jeastel | bar: October 2 to October 3
| 4. Profile Page | In Progress | 09/28/2024 |  | 12/13/2024 | Russell
| 5. Messages Page | To Do | 09/28/2024 |  | 12/13/2024 | Hanz
6. Store Page
7. Cart Page
8. Payment Page