## Sheet1
GAMEHUB INVENTORY SYSTEM
Members:
Hanz Chester Bacus
Jeastel Mae Maratas
Russell Joshua Palma
Statuses
Todo | In-Progress | Completed | On-hold
| Deliverables | Status | Date Started | Date Finished | Due Date | Assignee | August |  |  |  | September |  |  |  | October |  |  |  | November |  |  |  | December
[7 empty] | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4
UI-UX
| Landing Page | Completed | 2024-09-28 | 2024-10-10 | 2024-11-02 | Palma | bar: September 3 to October 2
| Log-In Page | Completed | 2024-09-28 | 2024-10-10 | 2024-11-02 | Bacus | bar: September 1 to October 2
| - User | Completed | 2024-09-28 | 2024-10-20 | 2024-11-02 | Bacus | bar: September 1 to October 3
| - Admin | Completed | 2024-09-28 | 2024-10-20 | 2024-11-02 | Bacus | bar: September 1 to October 3
| Sign-Up Page | Completed | 2024-09-28 | 2024-10-10 | 2024-11-02 | Maratas | bar: September 1 to October 2
| Home Page | Completed | 2024-09-28 | 2024-10-15 | 2024-11-02 | Bacus | bar: September 4 to October 3
| - New | Completed | 2024-09-28 | 2024-10-15 | 2024-11-02 | Palma | bar: September 4 to October 3
| - Deals | Completed | 2024-09-28 | 2024-10-26 | 2024-11-02 | Palma | bar: September 4 to October 4
| - Active | Completed | 2024-09-28 | 2024-10-26 | 2024-11-02 | Maratas | bar: September 4 to October 4
| - Laptops | Completed | 2024-09-28 | 2024-10-15 | 2024-11-02 | Maratas | bar: September 4 to October 3
| - Phones | Completed | 2024-09-28 | 2024-10-26 | 2024-11-02 | Maratas | bar: September 4 to October 4
| - PC | Completed | 2024-09-28 | 2024-11-01 | 2024-11-02 | Bacus | bar: September 4 to November 1
| - Accessories | Completed | 2024-09-28 | 2024-11-01 | 2024-11-02 | Maratas | bar: September 4 to November 1
Active - Games
| - LOL | Completed | 2024-09-28 | 2024-11-02 | 2024-11-02 | Bacus | bar: September 4 to November 1
| - Cyberpunk | Completed | 2024-09-28 | 2024-11-01 | 2024-11-02 | Maratas | bar: September 4 to November 1
| - CS:GO | Completed | 2024-09-28 | 2024-11-02 | 2024-11-02 | Maratas | bar: September 4 to November 1
| - Fortnite | Completed | 2024-09-28 | 2024-11-11 | 2024-11-02 | Palma | bar: September 4 to November 2
| - EldenRing | Completed | 2024-09-28 | 2024-11-11 | 2024-11-02 | Palma | bar: September 4 to November 2
| - Valorant | Completed | 2024-09-28 | 2024-11-18 | 2024-11-02 | Palma | bar: September 4 to November 3
| - Apex | Completed | 2024-09-28 | 2024-11-18 | 2024-11-02 | Bacus | bar: September 4 to November 3
| Cart | Completed | 2024-09-28 | 2024-11-25 | 2024-11-02 | Palma | bar: September 4 to November 4
| Account | Completed | 2024-09-28 | 2024-11-25 | 2024-11-02 | Maratas | bar: September 4 to November 4
| - Profile | Completed | 2024-09-28 | 2024-11-25 | 2024-11-02 | Bacus | bar: September 4 to November 4
| - Orders | Completed | 2024-09-28 | 2024-11-25 | 2024-11-02 | Bacus | bar: September 4 to November 4
| - Your Cart | Completed | 2024-09-28 | 2024-11-25 | 2024-11-02 | Palma | bar: September 4 to November 4
| - Logout | Completed | 2024-09-28 | 2024-11-18 | 2024-11-02 | Maratas | bar: September 4 to November 3
FUNCTIONALITIES
| Landing Page | Completed | 2024-09-28 | 2024-10-15 | 2024-11-02 | Palma | bar: September 3 to October 3
| Log-In Page | Completed | 2024-09-28 | 2024-10-15 | 2024-11-02 | Bacus | bar: September 4 to October 2
| - User | Completed | 2024-09-28 | 2024-10-20 | 2024-11-02 | Bacus | bar: September 4 to October 3
| - Admin | Completed | 2024-09-28 | 2024-10-20 | 2024-11-02 | Bacus | bar: September 4 to October 3
| Sign-Up Page | Completed | 2024-09-28 | 2024-10-15 | 2024-11-02 | Maratas | bar: September 4 to October 2
| Home Page | Completed | 2024-09-28 | 2024-10-15 | 2024-11-02 | Bacus | bar: September 4 to October 2
| - New | Completed | 2024-09-28 | 2024-11-05 | 2024-11-02 | Palma | bar: September 4 to November 1
| - Deals | Completed | 2024-09-28 | 2024-11-05 | 2024-11-02 | Palma | bar: September 4 to November 1
| - Active | Completed | 2024-09-28 | 2024-11-20 | 2024-11-02 | Maratas | bar: September 4 to November 3
| - Laptops | Completed | 2024-09-28 | 2024-11-05 | 2024-11-02 | Maratas | bar: September 4 to November 1
| - Phones | Completed | 2024-09-28 | 2024-11-20 | 2024-11-02 | Maratas | bar: September 4 to November 3
| - PC | Completed | 2024-09-28 | 2024-11-20 | 2024-11-02 | Bacus | bar: September 4 to November 3
| - Accessories | Completed | 2024-09-28 | 2024-11-28 | 2024-11-02 | Bacus | bar: September 4 to October 3
Active - Games
| - LOL | Completed | 2024-09-28 | 2024-11-28 | 2024-11-02 | Bacus | bar: September 4 to November 4
| - Cyberpunk | Completed | 2024-09-28 | 2024-11-05 | 2024-11-02 | Maratas | bar: September 4 to November 1
| - CS:GO | Completed | 2024-09-28 | 2024-11-05 | 2024-11-02 | Maratas | bar: September 4 to November 1
| - Fortnite | Completed | 2024-09-28 | 2024-11-28 | 2024-11-02 | Palma | bar: September 4 to November 4
| - EldenRing | Completed | 2024-09-28 | 2024-11-20 | 2024-11-02 | Palma | bar: September 4 to November 3
| - Valorant | Completed | 2024-09-28 | 2024-11-20 | 2024-11-02 | Palma | bar: September 4 to November 3
| - Apex | Completed | 2024-09-28 | 2024-11-20 | 2024-11-02 | Bacus | bar: September 4 to November 3
| Cart | Completed | 2024-09-28 | 2024-12-02 | 2024-11-02 | Palma | bar: September 4 to December 1
| Account | Completed | 2024-09-28 | 2024-11-28 | 2024-11-02 | Maratas | bar: September 4 to November 4
| - Profile | Completed | 2024-09-28 | 2024-12-02 | 2024-11-02 | Bacus | bar: September 4 to December 1
| - Orders | Completed | 2024-09-28 | 2024-12-02 | 2024-11-02 | Bacus | bar: September 4 to December 1
| - Your Cart | Completed | 2024-09-28 | 2024-12-02 | 2024-11-02 | Palma | bar: September 4 to November 1
| - Logout | Completed | 2024-09-28 | 2024-11-01 | 2024-11-02 | Maratas